## Electric Utility Service Connection

Effective:  July 1, 2025

Description.  This item shall consist of payment for work performed by the Electric Service Provider (Utility Company) in providing or modifying electric service as indicated.  THIS MAY INVOLVE WORK AT MORE THAN ONE ELECTRIC SERVICE LOCATION.

CONSTRUCTION REQUIREMENTS

General.  It shall be the Contractor's responsibility to contact the Electric Service Provider.  The Contractor shall coordinate his work fully with the Electric Service Provider both as to the work required and the timing of the installation.  No additional compensation will be granted under this or any other item for extra work caused by failure to meet this requirement.

For those locations served by ComEd; please contact ComEd, New Business Center Call Center, at 866 NEW ELECTRIC (1-866-639-3532) to begin the service connection process.  The Call Center Representatives will create a work order for the service connection.  The representative will ask the requestor for information specific to the request.  The representative will assign the request based upon the location of project.

For locations served by other electric service providers, that utility shall be contacted.

The Contractor should make particular note of the need for the earliest attention to arrangements with the Electric Service Provider for service.  In the event of delay by the Electric Service Provider, no extension of time will be considered applicable for the delay unless the Contractor can produce written evidence of a request for electric service within 30 days of execution.

Documentation.  The Contractor shall provide copies of all correspondence with the Electric Service Provider including as a minimum:

- A copy of the request for service to the Electric Service Provider.

- Service Entrance Sketch

- Electric Service Account Number

- Electric Meter Number

- Size of Utility transformer and available fault current.

- GPS coordinates of the service, format as described in the General Electrical Provisions.

All correspondence for State owned and maintained installations must include the pertinent contract number and Electrical Maintenance database number

Certain state-maintained electrical systems may have energy paid by local agencies, but unless otherwise established, energy billing for state-maintained electrical systems shall be directed to:

Illinois Department of Transportation

District 1

201 West Center Court

Schaumburg, Illinois 60196

Attn: Financial Services

Electric service correspondence for Non-State owned systems shall be directed to the respective agency assuming maintenance with a copy of the final service agreement submitted to IDOT.

Method Of Payment.  The Contractor will be reimbursed to the exact amount of money as billed by the Electric Service Provider for the services. Work provided by the Contractor for electric service will be paid separately as described under ELECTRIC SERVICE INSTALLATION.  No extra compensation shall be paid to the Contractor for any incidental materials and labor required to fulfill the requirements as shown on the plans and specified herein.

For bidding purposes, this item shall be estimated as $

Basis Of Payment.  This work will be paid for at the contract lump sum price for ELECTRIC UTILITY SERVICE CONNECTION which shall be reimbursement in full for electric utility service charges.

Designer Note:

The estimated cost of the electric service connections for bidding purposes shall be provided by the Designer or Design Consultant.

At the time this SP was written, the following municipalities have their own municipal electric utility: St. Charles, Winnetka, Naperville, Geneva, Batavia.

H:\SP\ELE\ElectricUtilityServiceConnection.doc