## Electric Utility Service Connection (ComEd)

Effective:  January 1, 2012

Description.  This item shall consist of payment for work performed by ComEd in providing or modifying electric service as indicated.  THIS MAY INVOLVE WORK AT MORE THAN ONE ELECTRIC SERVICE.  For summary of the Electrical Service Drop Locations see the schedule contained elsewhere herein.

CONSTRUCTION REQUIREMENTS

General.  It shall be the Contractor's responsibility to contact ComEd.  The Contractor shall coordinate his work fully with the ComEd both as to the work required and the timing of the installation.  No additional compensation will be granted under this or any other item for extra work caused by failure to meet this requirement.  Please contact ComEd, New Business Center Call Center, at 866 NEW ELECTRIC (1-866-639-3532) to begin the service connection process.  The Call Center Representatives will create a work order for the service connection.  The representative will ask the requestor for information specific to the request.  The representative will assign the request based upon the location of project.

The Contractor should make particular note of the need for the earliest attention to arrangements with ComEd for service.  In the event of delay by ComEd, no extension of time will be considered applicable for the delay unless the Contractor can produce written evidence of a request for electric service within 30 days of execution.

Method Of Payment.  The Contractor will be reimbursed to the exact amount of money as billed by ComEd for its services. Work provided by the Contractor for electric service will be paid separately as described under ELECTRIC SERVICE INSTALLATION.  No extra compensation shall be paid to the Contractor for any incidental materials and labor required to fulfill the requirements as shown on the plans and specified herein.

For bidding purposes, this item shall be estimated as $

Basis Of Payment.  This work will be paid for at the contract lump sum price for ELECTRIC UTILITY SERVICE CONNECTION which shall be reimbursement in full for electric utility service charges.

Designers Note:  The estimate of cost of service connections for bidding purposes shall be provided by the Designer or Design Consultant.

H:\SP\ELE\ElectricUtilityServiceConnection.doc