# 5F

# BRIDGE DECK LATEX OR MICROSILICA CONCRETE OVERLAY, CUT OFF DATE

(Effective April 5, 2024)

Placement of concrete for latex or microsilica overlays shall be between April 15 and October 15 unless approved, in writing, by the Engineer.

DESIGNER NOTE:

This work must also include a completion date no later than November 15 or a traffic control special provision requiring the Contractor to schedule his operations so that all traffic lanes are open from December 1 to March 1. This is per a request from Project Implementation to eliminate lane closures/reductions over winter months.