Memorandum

To:	Studies & Plans Squads                    PPM 10-04

From:	Jeff Birch                                 Revised:  Scott Neihart

Subject:	Working Day Computations

Date:	November 26, 1997                 Revision Date: April 1, 2016

PLAN PREPARATION MEMORANDUM 10-04

Working day computations should be performed in accordance with

Section 66-2.03, Construction Time Estimates of the BDE Manual.

In addition to the guidelines given in Chapter 66 of the BDE Manual, all Working Day computations shall be supported by a Time Bar Chart.

The “Estimate of Time Required” Form BDE 220A and the Time Bar Chart should be reviewed by the applicable District Bureaus at the same time they are reviewing the proposed plans.  The reviewed documents should become part of the squads’ permanent files.

As with all contracts, the designer must use their best judgment in determining what the appropriate rate of production is for any particular item.  The following is a suggested list of resources to be used when computing working days:

- Chapter 66 of the BDE Manual; Section 66-2.03 Construction Time Estimates

- Section 108 of the Standard Specifications

- District 5 Production Rates (Use in conjunction with BDE Chapter 66)

- Number of Accumulated Working Days for Conversion To a Completion Date and Calendar Days (work days “year”)

- Program Development Project Engineer’s judgment

- Example  “Time Bar Chart” and “Working Days 200?” may be found at Studies and Plans (s:)/Phase II Plans /Forms

DISTRICT FIVE PRODUCTION RATES

Based on research of two typical resurfacing projects.

Major		Sub

Worktype	Worktype	Description		    Unit		Low	High

Gravel or Crushed

Roadway	Aggregate	Stone Shoulders (wedge)	Ton		900	1200

Roadway	Excavation	Channel Excavation	Cu. Yd.		500	  800

Earth Excavation

Roadway	Excavation	(Shoulders & Widening)	Cu. Yd.		1000	1600

Roadway	Patching		Class A			Sq. Yd.		  100	  150

Roadway	Patching		Class B			Sq. Yd.		  100	  150

Roadway	Patching		Class C & D		Sq. Yd.		  100	  250

Roadway	Patching		Partial depth		Sq. Yd.		  240	  360

Bituminous Mixture

Roadway	Patching		for Patch		Ton		  40	    60

Bituminous Concrete

Roadway	Paving		Bind. & Surf. Course(Urban)  Ton		500	1500

Bituminous Concrete

Roadway	Paving		Surface (Rural)		Ton		1500	1800

Bituminous Concrete

Roadway	Paving		Binder Course (Rural)	Ton		1600	2000

Roadway	Paving		Bituminous Shoulders	Sq. Yd.		10000	15000

Roadway	Paving		Level Binder (Urban)	Ton		1000	1500

Roadway	Paving		Leveling Binder (Rural)	Ton		1300	1500

DISTRICT FIVE PRODUCTION RATES

Major		Sub

Worktype	Worktype	Description		   Unit		Low	High

Strip Reflective

Roadway	Paving		Crack Control		Ft.		20000	30000

Raised Reflective

Roadway	Pvt. Mk.		Pavement Markers	Each		  350	  500

Thermoplastic Pavement

Roadway	Pvt. Mk.		Marking (Truck)		Ft.		50000	60000

Bituminous Surface

Roadway	Removal		Removal (Urban)		Sq. Yd.		2000	10000

Bituminous Surface

Removal (Rural profile

Roadway	Removal		milling)			Sq. Yd.		30000	45000