# INSTALLATION OF TEMPORARY CONCRETE BARRIERS AND/OR TEMPORARY BRIDGE RAIL

Effective:  May 18, 1993					Revised:  November 1, 2006

The following procedure and traffic control shall be used for the placement, relocation, and removal of temporary concrete barrier and/or temporary bridge rail on this project:

A.	Placement of Temporary Concrete Barrier and/or Temporary Bridge Rail:

1.	Erect Traffic Control and Protection Standard 701321 as shown on the plans for Stage 1 Construction except for the temporary concrete barrier and/or temporary bridge rail.

2.	Place the temporary traffic signals in the red flash mode.

3.	Close the Stage 1 Construction lane to traffic and route two-way traffic over the Stage 1 traffic lane.  One flagman will be required at each end of the lane closure, at all times, to direct traffic.

4.	Erect the temporary concrete barrier and/or temporary bridge rail in the Stage 1 location, beginning at the approach end of the lane closure and proceeding to the departure end.

B.	Relocation of Temporary Concrete Barrier and/or Temporary Bridge Rail:

1.	When Stage 1 Construction is complete, relocate temporary concrete barrier tapers parallel to the roadway centerline beginning at the departure end and proceeding to the approach end.  Place cones at 25 ft (8 meters) centers to establish temporary tapers to close the Stage 2 Construction lane to traffic and route traffic over the Stage 2 traffic lane.

2.	Place the temporary concrete barrier and/or temporary bridge rail in the Stage 2 location starting with the approach end and proceed to the departure end.

3.	This procedure shall be followed for any adjustment of temporary concrete barrier and/or bridge rail during any stage.

C.	Removal of the Temporary Concrete Barrier and/or Temporary Bridge Rail:

1.	When Stage 2 Construction is completed, remove the temporary concrete barrier and/or temporary bridge rail beginning at the departure end of the lane closure and proceeding to the approach end.  Place cones at 25 ft (8 meters) centers to delineate the closed lane until all the temporary concrete barrier and/or bridge rail is removed.

2.	Remove the Traffic Control and Protection Standard 701321 and route two-way traffic over the structure.

D.	Additional Requirements During Placement, Relocation, and Removal of Temporary Concrete Barrier and/or Temporary Bridge Rail:

1.	One lane of traffic shall be maintained at all times.

2.	Men and equipment will not be permitted to encroach on the lane open to traffic.

3.	Any length of temporary concrete barrier and/or temporary bridge rail not complete in one-day time period shall be protected by barricades with steady-burning lights at 25 ft (8 meters) centers until the barrier work is complete.  A temporary attenuator shall be placed on the end of any length of temporary concrete barrier and/or temporary bridge rail not completed.

4.	Traffic control devices, as specified on the plans for Traffic Control and Protection Standard 701321 shall be placed on all temporary concrete barrier and/or temporary bridge rail in use overnight.

The cost of complying with this procedure shall be considered included in the cost of TEMPORARY CONCRETE BARRIER, RELOCATING TEMPORARY CONCRETE BARRIER, and/or TEMPORARY BRIDGE RAIL outlined in the plans.