## D1 Design spec usage guide
Bureau of Design Checklist & Use Guide
2026-01-16
| Designer: |  |  | FA Rte:
| Contract No.: |  |  | Job #:
| File Name | Specification Title | Effective | Revised | Comments | Requires | Changes *
| 104. Maintenance of Roadways.docx | Maintenance of Roadways | 1985-09-30 | 1996-11-01 | Insert into all contracts except certain D1 Maintenance contracts that do not include any pay items for concrete or HMA pavement work; i.e. Sweeping, Guardrail Repair, Bridge Painting, Crack and Joint Sealing, etc. Once the Contractor begins work they will assume responsibility for the maintenance of the pavement in the traveled lanes except for snow removal.
| 104. Status Of Utilities.docx | Status Of Utilities (D-1) | 2016-06-01 | 2025-04-01 | Insert into all contracts. The use of the phrase "To be determined" or "No dates set as of ____" is NOT acceptable information. It is very important that we have the most up to date information available for the contractor to avoid delay costs. For D1 Design projects please work with the D1 Design utility unit to get exact timeframe for utilty relocation. For Bureau of Local Roads (BLRS) led projects please provide a copy of the utility coordination correspondence with Prefinal and PSE submittal. |  | 1/24/13 Added 90 day compliance rule, revised start/completion dates to duration to complete relocation/adjustment. 10/11/19 updated to revise some of the table headings to better align with their intended purpose as well as minor revisions to the text. Revised: January 1, 2020 - Changed "Action" column in Utilities to be adjusted section to read "Duration of time" to better align with the purpose intended. - Removed "Address" field from entire spec. - Removed "Action" column from Utilities to be watched and protected section as it is not needed since language is already in the paragraph for the section. - Fixed some text input selections for better readability. Revised 10/16/24 Added text to contact IDOT Contractor for location of facilities. Revised 4/1/25 to clarify who is responsible for location of facilities.
| 105. Construction Layout Special for resurfacing with ADA and stand alone ADA.docx | Construction Layout Special for resurfacing with ADA and stand alone ADA (D1) | 2017-01-01 | 2017-04-17 | Insert into all contracts when construction layout is to be performed by the contractor for ADA work on resurfacing contracts or on stand-alone ADA contracts. Do not use any other special provision or Recurring check sheet special provision for construction layout in conjuction with this. | Project Specific ADA details must be provided in the plans with this special provision. | A new pay item X0320050 CONSTRUCTION LAYOUT (SPECIAL) has been created to be used with this special provision. Revised on April 2017 to address minor comments from industry.
| 107. Public Convenience and Safety.docx | Public Convenience and Safety (D-1) | 2012-05-01 | 2012-07-15 | Insert into all contracts that have roadway work |  | Revised 7/15/12 revised table and Holiday start times to “allow motorist travelling before Thanksgiving relief from any construction”
| 107. Tollway Permit and Bond.docx | Tollway Permit and Bond | 1989-01-13 |  | Use on any contract that needs access to any Illinois Tollway property; e.g. Advanced Warning Sign setup, Traffic Control on a Toll road, etc. The Contractor is required to secure the appropriate permits from the Illinois Tollway. Typically this will be required for any work within Tollway ROW or any lane closures on the Tollway. The Contractor is required to secure the appropriate permits from the Illinois Tollway prior to initiating any lane or ramp closures. | Send Plans to Tollway to review.
| 108. Completion Date Plus Working Days.docx | Completion Date Plus Working Days | 1985-09-30 | 2007-01-01 | Use on all Projects that need to be finished by a specific Completion Date. May also include Interim Completion Dates; typically 5 to 15 working days for landscaping, bridge painting, surveillance loops, and other items that cannot be completed due to calendar day or seasonal restrictions and are not included in the completion date for opening the roadway to traffic. Do not use in conjuction with BDE working day spec. Discuss with IDOT project manager on the use of this spec vs working day spec. Consider lead time of agency/railroad approvals, utility relocation, and equipment acquisition before selecting the final completion date. | Must fill in this special provision. Insert the work items and date to be completed in the spec. | Updated to 2007 Standard Specifications; eliminated term "Guaranteed" working days
| 108. Failure to Complete Work on Time.docx | Failure to Complete the Work on Time | 1985-09-30 | 2007-01-01 | Use if larger liquidated damages are desired beyond amount listed in Art 108.09. Designer’s Note: The Special Provision should not be used unless the amount of liquidated damages is greater than the amount listed in Article 108.09 of the Standard Specifications or Central Office Inserted Specifications. Typically used on larger high profile projects with aggressive schedules. Requires approval from IDOT project manager to use this special provision. | Fill in dollar amounts in the spec. | Updated to 2007 Standard Specifications; eliminated term "Guaranteed" working days
| 108. Incentive Payment Plan.docx | Incentive Payment Plan | 1995-10-01 | 2007-01-01 | Provides finacial incentive to the Contractor to complete the work ahead of schedule. Requires approval from IDOT Bureau Chief to use this special provision. BLRS project will require central office approval. | (1) Fill in dates and incentive/disincentive payment amounts in Table A. (2) Fill in the date for incentive payment completion date in last paragraph. | Updated to 2007 Standard Specifications; eliminated term "Guaranteed" working days
| 202. Lightweight Cellular Concrete Fill.docx | Lightweight Cellular Concrete Fill (D-1) | 2001-11-11 | 2018-06-18 | Use as recomended by D1 Bureau of Materials Geotechnical Engineer. Do NOT use BBS version of this special provision GBSP87 |  | 1/1/10 Replaces "Engineered Fill"; 1/20/10 changed Basis of Payment from Cu Ft to Cu Yd; 2/28/13 New approved foaming agent list, clarified calibration procedure; Revised 2/1/16 from New GBSP87 to a D-1 special that specifies 2 mixes and requirements, Qc sampling, limits equipment over Lightweight Cellular Concrete Fill until proper tests are acceptable; Revised 6/18/18 to show 4 mixes with min strength requirements, eliminate DCP requirement parameters; 8/13/18 revised to follow the mixes on GBSP78 while maintaining D-1 strength range requirements.
| 205. Embankment I.docx | Embankment I | 2011-03-01 | 2013-11-01 | Use as recommended in Geotechnical Report by D1 Bureau of Material's Geotechnical Section; |  | Revised 6/28/13 to reference the BMPR Policy Memo “RAP for Aggregate Applications”, control deleterious in RAP
| 205. Embankment II.docx | Embankment II | 2011-03-01 | 2013-11-01 | Use as recommended in Geotechnical Report by D1 Bureau of Material's Geotechnical Section; |  | Revised 6/28/13 reference BMPR Policy Memo “RAP for Aggregate Applications”, control deleterious in RAP
| 400. Temporary Pavement.docx | Temporary Pavement | 2003-03-01 | 2008-04-10 | Use if temporary pavement is needed for traffic control. Designer Note: Follow the approved Phase 2 Pavement Design memo. This memo is requested by the Designer when MOT plans have been established. Make sure to include temporary pavement items with HMA mixes in the HMA Mixture Requirement Table. Bureau of Local Roads led projects without an IDOT roadway will not have this memo. When PC Temporary Pavement is used as an option, the following note shall appear on the plans adjacent to the HMA Mix Table: “PC concrete temporary pavement shall consist of Class PV Concrete meeting the requirements of Art. 1020 of the Standard Specifications, PCC pavement X' thick. Temporary PCC pavement does not require dowel bars.” Verify with the pavement design memo if the following note and associated pay item is needed: "All Temporay Pavement shall be provided over 4" SUBBASE GRANULAR MATERIAL TYPE B." For quantity estimation purposes, excavation quantities should be estimated assuming the thicker design if both design options are being shown in the plans. If you need a temporary pavement that has more specific details then you will need to write your own version of “Temporary Pavement (Special)”. | If the pavement design memo states the Contractor to have both HMA and PC options, mixes on HMA Mixture Table AND PC note must be shown on the plans | 4/10/08 Updated to 2007 Standard Specifications; ie HMA; removal optional
| 402. Aggregate Surface Course for Temporary Access.docx | Aggregate Surface Course for Temporary Access | 2001-04-01 | 2007-01-02 | Use in all contracts that will disturb access to entrances and/or roads and temporary access needs to be provided. Contractor is to construct and maintain temporary access to private, commerical, and road entrances/driveways. Note that this work is paid for in units of EACH. |  | Updated to 2007 Standard Specifications; corrected Basis of Payment back to Each
| 406. HMA Binder and Surface Course.docx | HMA Binder and Surface Course (D-1) | 2019-11-01 | 2026-01-16 | Insert into all HMA contracts. Do not USE BDE version of this spec. This special provision was created to comply with the revised standard and designed overlay policies based on the new Transportation Asset Management Plan (TAMP). The special provision includes specifications for the oscillatory roller and longitudinal joint testing. |  | Released 8/2019 This special replaces the D1 spec “HMA Mixture Design Requirements (D-1)”. Revised from the BDE version to maintain the D1 mix and tests specifications; Revised 12/5/19 to eliminate the option to use Elvaloyfor the IL-4.75 mix; Revised to include CM13 4/ for IL-9.5 E Mix. 10/14/20 revised to remove Tensile Strength Ratio and Hamburg Wheel verification requirements which are now covered in the BDE spec “HMA Mixture Design Verification and Production (Modified for I-FIT)(D-1)”. 11/13/20 Removed the verification testing language and minor editorial changes to Test Strip. 12/1/21 Revised to keep the district’s mixture requirements, test strip testing process and special roller requirements as well as additional editorial revisions. Revised 1/1/26 to add items based on a new BDE spec (binder mix placement between seasons, test strip evaluation). Revised 1/16/26 per revision of BDE special.
| 406. Pavement Rehabilitation by Hot In-Place Recycling.docx | Pavement Rehabilitation by Hot In-Place Recycling | 2003-07-11 | 2014-05-05 | Use as recomended by D1 Bureau of Materials. Design footnote: If provided as a pay item, the preparation of the base will be paid for in accordance with Article 358.07. If not provided as a pay item, preparation of the base beyond cleaning will be paid for in accordance with Article 109.04. |  | Replaces "Level Binder - Pavement Rehabilitation by Hot In-Place Recycling", Hot_In-place_Recycling.doc; last revised 4/20/04; updated to 2007 Standard Specifications; 12/1/11 separate pay items for Pvmt Marking Removal & RRPM Removal; Revised 5/5/14 clarify payment for Pvmt Marking & RRPM removal
| 406. Winterized Temporary Access.docx | Winterized Temporary Access | 2012-01-01 | 2012-03-05 | The special provision is only to be used on projects that have temporary access through a Construction Zone that needs to be maintained over the winter due to staging. It addresses a Bureau of Construction concern about damage to property due to aggregate being ejected from plows over the winter months. This special provision addresses maintaining temporary access for private and commercial entrances and roads (e.g. “alleys”) on projects lasting longer than one construction season. Plans should clearly identify by way of schedule of quantities or plan labeling how the quantities were figured out. The plans and/or schedule intention is to help the contractor understand the Department thought process so that they can properly place a fair/reasonable bid. It should be used in conjunction with the District spec Aggregate Surface Course for Temporary Access. |  | 2/22/12 modified temporary aggregate access for staging over the winter months, use in conjunction w/Aggregate Surface Course for Temporary Access; 3/5/12 revised pay item from WINTERIZED TEMPORARY ACCESS to TEMPORARY ACCESS (WINTERIZE) per Springfield
| 424. Detectable Warnings (Special) in City of Chicago.docx | Detectable Warnings (Special) in City of Chicago | 2017-07-20 |  | Insert into all contracts that have detectable warnings within the City of Chicago. This requires the contractor to use cast iron detectable warnings. Use pay item "Detectable Warnings (Special)", X4240800 | Use with D1 CADD Detail BD-58 "City of Chicago Detectable Warnings"
| 440. Pavement Removal, Special.docx | Pavement Removal, Special | 1989-01-13 | 2007-01-01 | This pay item should be used only when it is necessary to remove pavement over an old water main or similar utility where the vibration of normal pavement removal operations could cause damage to the utility. 44004400 PAVT REMOVAL SPL SQ YD M4402550 PAVT REMOVAL SPL SQ M |  | Updated to 2007 Standard Specifications
| 442. Class D Patches (SPECIAL) | Class D Patches (SPECIAL) | 2020-07-24 |  | Used in cases where a surface mix needs to be included as part of the patching item. Typically, for areas to be patched outside of resurfacing limits. | Requires mixes to be shown in the HMA Mixture Table on the plans.
| 481. Grading and Shaping Shoulders.docx | Grading and Shaping Shoulders | 2001-12-28 | 2007-01-01 | Include in all resurfacing contracts that require Aggregate Wedge Shoulder |  | Updated to 2007 Standard Specifcation format
| 502. Cofferdam (Type 1) (In-Stream Wetland Work).docx | Cofferdam (Type 1) (In-Stream/Wetland Work) (D-1) | 2019-01-01 | 2022-08-15 | Insert into all contracts that require a Section 404 Permit from the US Army Corps of Engrs. clarifies the use of Cofferdams (Type 1) for in-stream and/or wetland work within jurisdictional wetlands and Waters of the US. The work will be paid for at the contract unit price of Each for COFFERDAM (TYPE 1) (IN-STREAM/WETLAND WORK) and will be measured for payment in units of Each where Each is defined as a plan detailed stage of bridge, culvert, or other construction for which a temporary in-stream cofferdam(s) is required. If staged construction is not detailed/specified on the plans, this work will be measured as a total of One Each. | The designer is required to show the flow requirements (including the 2-year) on the plans for work on the site. Also include appropriate 404 Permit General Note. | Updated to reference the Standard Specifications for Road and Bridge Construction as well as the new US Army Corps of Engineers' Nationwide Permit Program.
| 502. Rock Excavation for Structures, Special.docx | Rock Excavation for Structures, Special | 1985-09-30 | 2007-01-01 | Use if Rock Excavation is needed for storm sewer jacked in place based on Geotechnical report. 50200410 ROCK EXC STRUCT SPL CU YD M5020410 ROCK EXC STRUCT SPL CU M |  | Updated to 2007 Standard Specifications; 11/7/08 added "of the Standard Specifications" without changing revised date
| 503. Concrete Noise Abatement Walls (Absorptive & Reflective).docx | Concrete Noise Abatement Walls (Absorptive & Reflective)(Dist 1) | 2008-09-05 | 2018-12-18 | Include in all contracts that require noise walls in District One; Designer Notes Additional consideration should be given for the color of stain and the pattern utilized on the receiver side of the noise wall. During Phase II outreach, the ability to choose preferences should be solicited from affected local communities. Location information will be conveyed using Table 1 in this special provision. If a local agency requests additional aesthetic treatments beyond the base noise wall, the local agency will be responsible for 100 percent of this cost increase. Overhead power lines present in the vicinity of proposed noise wall locations will necessitate the inclusion of a special provision addressing Grounding of Steel Posts for Concrete Noise Walls. This Special Provision contains two separate fill-in-the-blank fields: Table 1 in the Design Criteria section and in the Materials section. The intent of Table One is to clearly convey the exact location, side, and material type of each wall to be constructed. The table should be expanded / contracted as the project dictates. Noise Wall Number (Column 1) is used as reference, correlating to the Project Report. Two entries are provided for Stationing (Columns 2 & 3), intended for each Side of the Wall (Column 4); Expressway side, Main Route side, Frontage Rd side or Residential side. Noise Reduction Coefficient (NRC; Column 5), should correlate to the Side of the Wall in the absorptive condition: Frontage Road = 0.80, Residential = 0.65. Comments (Column 6) are allowed to explain if absorptive, reflective, or a composite wall is specified for the area. The current pattern used on the side facing the State maintained route is a rolled Ashlar Stone finish used in section "Materials (k)". | Fill out Noise Abatement Wall (NAW) Table with location, Side and Noise Reduction Coefficient (NCR). Contractor to coordinate with D1 Roadside Development with sample of the colors, textures and patterns proposed for use on the project for approval. | 10/5/09 included BBS comments; 6/25/10 revised Design Section to more closely match BBS section & revised paint spec to paint galvanized steel; added Ashlar Stone to Materials (j); 7/1/10 Revised shaft reinforcement paragraph & Noise Wall Side Conditions in table; 7/25/10 Revised Materials Section subparagraphs (c), (d) & drilled shaft reference since Sect 516 already referenced in Design Section; 1/12/11 revised Materials subparagraph (d) to "or" to have 3 tests; 12/18/18 Revised point of contact person to Giovanna Zaffina
| 522. Rustication Finish For Retaining Walls.docx | Rustication Finish For Retaining Walls | 1990-05-01 | 2007-01-01 | Use if needed to provide a rustification finish on face of proposed reinforced concrete retaining walls using formliners. 50300510 RUSTICATION FINISH SQ FT M5030380 RUSTICATION FINISH SQ M | Use with D1 CADD Detail BD-28 "Rustification Finish& Geocomposite Drain For Retaining Walls" | Updated to 2007 Standard Specification format
| 550. Storm Sewer Adjacent to or Crossing Water Main.docx | Storm Sewer Adjacent to or Crossing Water Main | 1996-02-01 | 2007-01-01 | Use when both of the following conditions exist: 1) Horizontal separation of storm sewer is closer than 10 ft (3 m) to a water main. 2) Vertical separation when: A. Storm sewer crosses over a water main or B. Storm Sewer is adjacent or below water main but is within 18" | All required locations must be shown in the plans. | Updated to 2007 Standard Specifications
| 550. Storm Sewers & Sewer Connections to City of Chicago Sewers.docx | Storm Sewers & Sewer Connections to City of Chicago Sewers | 1985-09-30 | 2021-03-10 | Use on any project within the City of Chicago that includes storm sewer work. It specifies that all storm sewers and sewer connections 21 inches in diameter and smaller shall be best quality tile socket pipe conforming to the specifications for Extra Strength Clay Pipe, ASTM C 700. DESIGNERS NOTE: The only other sewer pipe the City of Chicago will allow for sewers 21 inches in diameter or less is ductile iron pipe Class 52 with push-on or mechnical joints. Ductile iron pipe should not be used unless a specific problem has been identified. |  | Updated to 2007 Standard Specifications
| 600. Slotted Drain.docx | Slotted Drain | 1985-09-30 | 2007-01-01 | Use if slotted drains are needed to catch sheet flow water before it heads towards driveways or loading docks. The slot height is currently available in either 2-1/2 inches (62.5 mm) or 6 inches (150 mm). Before specifying any other slot height, the designer must verify availability |  | updated 11/01/96; updated for 2007 Standard Specifications; 11/7/08 added "of the Standard Specifications" without changing revised date
| 602. Cleaning Existing Drainage Structures.docx | Cleaning Existing Drainage Structures | 1985-09-30 | 2022-05-01 | The spec is intended to be used to clean drainage structures and storm laterals that typically range from 12 inches to 24 inches. When size of existing sewer to be cleaned is known then pay items for cleaning individual sizes of storm sewer should be used. in the SOQ this pay item should be shown as non-federally eligible (100% state or 100% local funded). | Typically required on most resurfacing and intersection improvement projects that have closed drainge system | Updated to 2007 Standard Specifications, 11/7/08 added "of the Standard Specifications" without changing revised date; revised12/1/11 revised Storm Sewers to be Cleaned to include diameter in Pay Item; rev'd 5/1/22 to specify locations determined in field by Engineer
| 603. Adjustments-Reconstructs.docx | Adjustments and Reconstructions | 2011-03-15 | 2021-10-01 | Use on projects with milling and resurfacing with frames/structures to be adjusted | Use with D1 CADD Detail BD-08 "Details for Frames and Lids Adjustments with Milling" | Deleted reference to "Class SI" concrete and replaced 72 hours with reference to Art 701.17(e)(3)b; added revision to Art 602.11(c); Class PP-2 will be used on all adjustments in lieu of HMA; unless otherwise noted in the plans.
| 603. Drainage and Inlet Protection Under Traffic.docx | Drainage And Inlet Protection Under Traffic (D-1) | 2011-04-01 | 2011-04-02 | Use on mill and resurface projects with inlets. This special provision was originally developed by the Central Bureau of Materials at the recommendation of the Illinois Highway Development Council to allow temporary rubber ramps to be used as an option around frames and grates during milling and resurfacing operations. It should be inserted into contracts involving milling and resurfacing on contracts with permanent posted speed limits up to 40 mph. |  | Modified BDE 60272; revised reference to "Class SI" concrete with "Class PP" and replaced 72 hours w/ reference to Art 701.17(e)(3)b;
| 606. Concrete Curb, Type B (Modified).docx | Concrete Curb, Type B (Modified) | 1985-09-30 | 2007-01-01 | Use when designer has a non standard Type B curb |  | updated 11/1/96; Updated to the 2007 Standard Specifications
| 606. Curb or Combination Curb and Gutter Removal and Replacement.docx | Curb or Combination Curb and Gutter Removal and Replacement (D-1) | 2020-01-01 | 2022-09-01 | Use on Contracts with various locations of deteriorated or damaged curb and gutter to be replaced in-kind; i.e. resurfacing, etc. Locations to be determinded by the RE. Do not use on reconstruction or widening projects which should have separate pay items for the C&G removal and the installation of new C&G of a specific type. This special provision was created to provide more clarity on the supporting text that was previously in BD-24. The special also provides additional direction on how to handle unsuitable material and differentiates between different lengths for more accurate contractor bidding. As such, two new pay items have been created for removal and replacement sections 10 feet or less as well as for sections greater than 10 feet in length. This special provision shall be inserted into all contracts that have curb or curb and gutter removal and replacement. It should be noted that the minimum removal and replacement section of curb or curb and gutter shall be 4 linear feet. The following pay items shall be used based on length of curb section being replaced: 10 FEET OR LESS (NEW PAY ITEMS): X4400221 - CURB REMOVAL AND REPLACEMENT LESS THAN OR EQUAL TO 10 FEET X4400501 - COMBINATION CURB AND GUTTER REMOVAL AND REPLACEMENT LESS THAN OR EQUAL TO 10 FEET OVER 10 FEET (NEW PAY ITEMS): X4400223 - CURB REMOVAL AND REPLACEMENT GREATER THAN 10 FEET X4400503 - COMBINATION CONCRETE CURB AND GUTTER REMOVAL AND REPLACEMENT GREATER THAN 10 FEET | Use with D1 CADD Detail BD-24 "Curb or Curb and Gutter Removal and Replacement" | 7/24/20 The CADD District Detail, BD 24, titled “Curb or Curb and Gutter Removal and Replacement” has been revised. For simplification and clarity, much of the supporting text that was previously shown in the detail has been removed. As a result, a new D-1 special provision has been created to contain these requirements. 9/1/22 New Pay Items were created and referenced in the special for removal and replacement greater than 10 feet.
| 606. Stabilized Median Surface.docx | Stabilized Median Surface | 1985-09-30 | 2017-03-02 | Use on contracts using the STABILIZED MEDIAN SURFACE pay item. |  | Updated to 2007 Standard Specifications; added "of the Standard Specifications" without changing revised date; 3/24/15 Revised to use HMA Surface Course, Mix “D”, N50; 3/2/2017 Revised to allow a Hot Mix Asphalt Mix D at N50 or N70 as appropriate.
| 637. Aggregate For Concrete Barrier (D-1).docx | Aggregate For Concrete Barrier (D-1) | 2004-03-11 | 2008-01-24 | Include in all contracts that include new permanent concrete barrier. Ensures correct aggregate quality to be used in pcc mix. |  | Updated for the 2007 Standard Specifications; 1/24/08 Revised Title from "Concrete Barrier" so there would be no confusion with BDE speciial provision with the same name.
| 670. Engineers Field Office Type A (D1).docx | Engineer’s Field Office Type A (D1) | 2022-01-01 |  | Use on all contracts with a Construction Cost Estimate below $10 million. |  | A new pay item X6700407 ENGINEER'S FIELD OFFICE TYPE A (D1) has been created to be used with this special provision.
| 670. Engineers Field Office Type A (Special) (D1).docx | Engineer’s Field Office Type A (Special) (D1) | 2011-12-01 | 2013-05-01 | Use on contracts with a Construction Cost Estimate $10 million and up.
| 701. Traffic Control & Protection (Arterials).docx | Traffic Control & Protection (Arterials) | 1996-02-01 | 2011-03-01 | Used for lump sum payment of traffic control and protection of Arterial Routes; including any detour signage, district traffic control standards, and state highway standards | Do not pay for highway standards seperately. Full maintenance of traffic control plans are required to use this special provision. Any exceptions to not provide MOT plan will need to get approved by IDOT Project Manager. | Revised 11/01/96; Updated to 2007 Standard Specification format; Revised 3/1/11 Incorporated Detour Special Provision; Revised title from "Work Zone Traffic Control (Lump Sum Payment)", used generic reference to temporary pavement markings; deleted temporarypavement marking from Basis of Payment, added to exception; added "Traff Ctrl & Prot (Expy)" to exception; revised file name from 901 to 701;
| 701. Traffic Control Plan.docx | Traffic Control Plan | 1985-09-30 | 2007-01-01 | Use on all contracts that require traffic control. | Designer to fill in all Highway Standards, District CADD Details and special provisions used pertaining to Traffic Control. | Last revised 10/1/05; Updated to 2007 Standard Specifications format
| 1004. Friction Aggregate.docx | Friction Aggregate (D-1) | 2011-01-01 | 2021-12-01 | Insert into all HMA contracts. |  | 10/11/13 Updated reference per changes in 2014 Supplemental; 7/24/15 Revised to restrict the use of crushed concrete and crushed gravel in Mix E and in SMA N80 mixes; 4/29/16 Revised to clarify SMA N80 dolomite use and restricted aggregate blending; 5/9/16 corrects a conflict it had with another special by clarifying aggregate types for SMA mixes. Revised 11/1/19 to remove "leveling" from Binder 9.5 description; 12/1/21 Editorial revisions to follow the 2022 Standard Specifications.
| 1005. Rockfill (D-1).docx | Rockfill | 2010-01-01 | 2022-04-01 | Use as directed by D1 Bureau of Materials Geotechnical Engineer. | Use with pay item Z0054400 ROCK FILL (CU YD)
| 1020. Slipform Paving.docx | Slipform Paving (D-1) | 2014-11-01 |  | Use on all PCC Paving contracts per Bureau of Materials. Only effective on contracts where a slip form paver is used. |  | 11/1/2014 Released to reinstate the 2012 limits for slump and air content for slipform paving; addresses the issues with edge slump
| 1021. Mineralized Carbon Dioxide Concrete (D-1).docx | Mineralized Carbon Dioxide Concrete | 2026-01-01 |  | Use on all contracts with pcc items, such as sidewalk, driveways, and curb & gutter. |  | 01/01/26 Released to add the specified product as an additive to concrete mixes for sidewalk, driveway and curb and gutter items. To be used at the option of the contractor.
| 1030. HMA - Mixture Design Verification & Production.docx | HMA – Mixture Design Verification & Production (D-1) | 2019-11-01 | 2026-01-01 | Insert into all HMA contracts. Do NOT use BDE version of this spec titled “HMA – Mixture Design Verification and Production (Modified for I-FIT Data Collection)”. |  | Revised 10/30/2020 from BDE for Jan 2, 2020, deleted test strip state spec. 11/13/20 Revised to eliminate TSR mix design verification samples, removed 3,000 ton requirement for test strip; guidance for test strip is in the HMA Binder and Surface Course (D-1) special provisions. D-1 will follow statewide verification and production parameters for TSR/Hamburg wheel/IFIT. Rev'd 7/1/21 Revised to show a two day window for I-FIT submittals of Low ESAL mixes to the lab. Do not use BDE 80406 HMA Mixture Production and Verification (Modified for IFIT). 12/1/21 Revised to keep the requirement that Contractor gyrated samples are to be submitted to the District lab. Revised 1/1/26 to add items on BDE special (production test evaluation).
| Available Reports (D1 LR) | Available Reports (D1 LR) | 2021-07-01 |  | Use on all Local Roads Contracts and check all applicable boxes. Do not use on Bureau of Design led contracts.
| LR800.01TS-TRAFFIC SIGNAL GENERAL REQUIREMENTS | TRAFFIC SIGNAL GENERAL REQUIREMENTS (D1 LR) | 2016-04-01 | 2016-06-20 | Use for BLRS projects that only have traffic signal work (including temporary timing) at non-IDOT intersections. Do not use on Bureau of Design led contracts.
REMOVED SPECIALS
| 300. Aggregate Subgrade Improvement.docx | Aggregate Subgrade Improvement (D1) | 2012-02-22 | 2021-12-01 | Use with aggregate subgrade pay item for subbase and for undercuts. Do not use BDE version. Specifies the 6" diamater stone that D1 requires for subbase and undercuts. If variance is needed then use Sub Base Granular Material Type B (need D1 Bureau of Materials/Geotech approval). The typical Aggregate Subgrade Improvement thickness to be used is 12”. The D1 Bureau of Material’s Geotechnical Engineer will advise Bureau of Design when to use other thicknesses and at what plan locations; e.g. in areas where there is removal of unsuitable material, etc. The typical unit of measurement to be used is SQ YD. The Cu Yd unit of measurement is to be used when recommended by the D1 Bureau of Material’s Geotechnical Engineer in areas of variable depth. The CuYd pay item is typically used for undercuts only. Do not use Aggregate Subgrade Improvement, 4” in District 1; special provision requirements cannot be met at this thickness. Use Subbase Granular Material, Type B or consult D1 Bureau of Material's Geotech Engineer. | Refer to geotechnical report for guidance on undercuts. All widening and reconstruction projects should consider adding nominal quantity for undercuts (CU YD) even when not specified in geotech report. | 2/22/12 District version to replace BDE 4/1/12 version; 8/1/12 Revised to clarify the basis of payment and capping aggregate; 1/1/13 use mechanically calibrated feeders, remove #200 from gradation; 5/31/13 added Note 3 to Materials section; 11/1/13 added Note 3 (Materials) to reference Policy and added 3rd point under GRADATION for deletirious materials; Revised 19/19/14 to eliminate the deleterious RAP count; 3/5/15 updated to eliminate the CS02 gradation, add calibration parameter for feeders, specify a non-mechanically blended RAP amount and clarify round gravel use; 12/1/21 Editorial revisions to follow the 2022 Standard Specifications.
| HAMBURG WHEEL AND TENSILE STRENGTH RATIO TESTING (D1 LR) | HAMBURG WHEEL AND TENSILE STRENGTH RATIO TESTING (D1 LR) | 2020-12-01 |  | Insert into all BLRS contracts that have HMA mix items. Do not use on Bureau of Design led contracts. |  | Created to complement the HMA B & S Crse (D-1) on local agency contracts -& restrict use of IFIT testing parameters
| 1030. Hot-Mix Asphalt (D-1).docx | Hot-Mix Asphalt (D-1) | 2022-01-01 | 2022-08-01 | Insert into all HMA contracts. Do NOT use BDE version o f this spec titled "Hot-Mix Asphalt".
| 1032. Ground Tire Rubber (GTR) Modified Asphalt Binder.docx | Ground Tire Rubber (GTR) Modified Asphalt Binder (D-1) | 2006-06-26 | 2021-12-01 | Insert into all HMA contracts |  | Only used when requested in 2009; adds to 2012 Standard Specification (Bit Mat & HMA) for 01/01/13, changed grades from 64-22 to 64-28 and added 58-28, deletes #8 req. and revised #16; use on all HMA contracts; Revised 4/1/16 to conform with Standard Specification 2016 book
| 107. CTA Flagging and Coordination.docx | CTA Flagging and Coordination | 1998-05-14 | 2009-08-27 | Use when the Contractor will be required to work on, over, or in close proximity of the CTA (Chicago Transit Authority) right-of-way and infrastructure | Send plans to CTA for review | Outdated spec. Removed on 1/5/23 per Lukasc coordination with RR unit. RR unit will insert as needed per RRPLI coordination.
| 208 Coarse Aggregate for Backfill, Trench Backfill and Bedding (D-1).docx | Coarse Aggregate for Backfill, Trench Backfill and Bedding (D-1) | 2011-11-01 | 2013-11-01 | Use whenever new storm sewer or pipes are to be installed under pavement. Do not use with backfill of electrical or signal work as larger rock specified may damage equipment. |  | Revised 6/28/13 reference to BMPR Policy Memo “RAP for Aggregate Applications”, and control deleterious in RAP. Removed on 1/19/24 since aggregate production has changed making this sp obsolete.
| 208. RAP for Non-Porous Embankment and Backfill.docx | RAP For Non-Porous Embankment and Backfill | 2001-04-01 | 2007-01-01 | Use in all contracts with embankment or backfill. |  | Removed 3/7/2025.