## Electric Service Installation and Connection

Effective:  August 1, 2025

Description.  This item shall consist of all material and labor required to extend, connect or modify the electric service, as indicated or specified, which is over and above the work performed by the Electric Service Provider (Utility Company). This item shall also consist of reimbursement for work performed by the Electric Service Provider in providing or modifying electric service as indicated.

CONSTRUCTION REQUIREMENTS

General.  It shall be the Contractor's responsibility to contact the Electric Service Provider.  The Contractor shall coordinate his work fully with the Electric Service Provider both as to the work required and the timing of the installation.  No additional compensation will be granted under this or any other item for extra work caused by failure to meet this requirement.

For those locations served by ComEd; please contact ComEd, New Business Center Call Center, at 866 NEW ELECTRIC (1-866-639-3532) to begin the service connection process.  The Call Center Representatives will create a work order for the service connection.  The representative will ask the requestor for information specific to the request.  The representative will assign the request based upon the location of project.

For locations served by other Electric Service Providers, that Electric Service Provider shall be contacted.

The Contractor should make particular note of the need for the earliest attention to arrangements with the Electric Service Provider for service.  In the event of delay by the Electric Service Provider, no extension of time will be considered applicable for the delay unless the Contractor can produce written evidence of a request for electric service within 30 days of execution.

The Contractor shall ascertain the work being provided by the electric utility and shall provide all additional material and work not included by other contract pay items required to complete the electric service work in complete compliance with the requirements of the utility.

Documentation.  The Contractor shall provide copies of all correspondence with the Electric Service Provider including as a minimum:

- A copy of the request for service to the Electric Service Provider.

- Service Entrance Sketch

- Electric Service Account Number

- Electric Meter Number

- Size of Utility transformer and available fault current.

- GPS coordinates of the service, format as described in the General Electrical Provisions.

All correspondence for State owned and maintained installations must include the pertinent contract number and Electrical Maintenance database number

Certain state-maintained electrical systems may have energy paid by local agencies, but unless otherwise established, energy billing for state-maintained electrical systems shall be directed to:

Illinois Department of Transportation

District 1

201 West Center Court

Schaumburg, Illinois 60196

Attn: Financial Services

Electric service correspondence for Non-State owned systems shall be directed to the respective agency assuming maintenance with a copy of the final service agreement submitted to IDOT.

Method Of Measurement.  Electric Service Installation and Connection shall be counted, each.

Basis Of Payment.

Any charges by the Electric Service Provider shall be approved by the Engineer and paid for as an addition to the Contract according to Article 109.05 of the Standard Specifications.

This work will be paid for at the contract price each for ELECTRIC SERVICE INSTALLATION AND CONNECTION which shall be payment in full for the work specified herein, excluding utility reimbursement.

Designer Note:

At the time this SP was written, the following municipalities have their own municipal electric utility: St. Charles, Winnetka, Naperville, Geneva, Batavia.